## Sheet1
Project Plan - Team Tilba Tilba | W3 | W4 | W5 | W6 | W7 | W8 | W9 | W10 | W11 | W12 | W13
Members: Jason, Anil, Jie, Harry
Project Plan Due | W4: 2017-03-29
Defining Scope | bar: W3 to W4
Find, Decide on Data Set | bar: W3 to W4
Define Purpose of Analysis | bar: W4
Getting Data Ready | bar: W4 to W5
Clean the data | bar: W4 to W5
Modifying the data | bar: W5
Data exploration | bar: W5
Modeling | bar: W5 to W7
Decide Modeling Methods | bar: W5 to W7
Running the Model | bar: W6 to W7
Results and Conclusion | bar: W7 to W10
Writing up results from models | bar: W7 to W10
Writing up conclusion and final review | bar: W7 to W10
DM Project Draft due | W10: 2017-05-15
Updating the Draft, final chance | bar: W10 to W12
DM Project Report due | W12: 2017-05-29
DM Project Poster due | W13: 2017-06-05